## Process_Review
Process | Purpose | Review Process | W-1 | W0 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8
Develop Questionnaire | bar: W-1 to W0
Incident Management | Minimize the impact of Incidents affecting the availability of services | Interview PM, Team Lead, Team Members,review IM tool | bar: W1 to W2
Configuration Management | Code assets are properly managed,controlled, accurate and reliable | Review CM artifacts, traceability,check-in, check-out process,prologue comments etc. | bar: W1 to W2
Checkpoint-1 | bar: W2
Change Management | Plan, test, coordinate,implement and monitor changes | Interview PM, Team Lead, Team Members,review CM tool,Review test cases,review deployment process | bar: W1 to W2
Problem Management | Identify, record, track,correct,manage problems, recognize recurring problems,addressing procedural issues | Interview PM, Team Lead, Team Members,review IM tool | bar: W3 to W4
Checkpoint-2 | bar: W4
Release Management and Deployment | Package in scope applications into Releases,deploy in scope applications | Review Release management process, | bar: W5 to W6
Knowledge Management | Retain knowledge, disseminate knowledge, KM portal, lessons learnt | Review AID,RCA documents, KM portal,CMDB etc. | bar: W5 to W6
Modernization |  | Review Devops process,Db process,UI,API etc. | bar: W5 to W6
Checkpoint-3 | bar: W6
Internal review of Client deck | bar: W7
Present Client Deck | bar: W8